## Guidance
Three Waters Stimulus Funding - Cash Flow Profile
1 | Guidance
This template was created to forecast the cash flow profile of Three Waters Stimulus funding injections against the estimated cash outflows of the Expenditure Programme.
The following principles were used to guide the approach to forecasting funding injections:
- Funding injections are received upon achievement of Programme milestones
- The milestones are linked to a % of funding spent, rather than activities, to allow flexibility in the Programme
- 50% of the allocated Stimulus funding is received upfront
- A contingency amount is held throughout and is to be received as a final payment at the end of the Water Reform period
- Funding injections are balanced against expected cash outflows as not to hold too much cash, but also not risk a funding gap and impact on workflow
2 | Formatting
2.1 | Cell Formatting
Input Assumption - for Council Input
2.2 | Sheet Formatting
Input and calculation sheets
Output Sheets
End

## Input
Three Waters Stimulus Funding - Cash Flow Profile
| Error Check | OK
| Funding Shortfall Check | OK
| Funding Shortfall | 0
1 | Funding | Quantity | % | $ | Guidance
| Reform Funding |  |  | 20 | Total funding to be received
| Upfront payment |  | 50% | 10 | % of funding received upfront
| Final payment |  | 1% | 0.2 | % of funding to be paid in final month of delivery
| Milestone Funding: Tranche 1 | 5 | 5% | 1 | % of funding to be received upon achieving milestone and number of milestones
| Milestone Funding: Tranche 2 | 5 | 4.8% | 0.96 | % of funding to be received upon achieving milestone and number of milestones
| Total |  | 100% | 20
| Check |  | 0% | 0
| Milestone Spend threshold %: Tranche 1 | 40% |  |  | % of project budget to be spent for milestone achievement. Can be entered at an individual project level below.
| Milestone Spend threshold %: Tranche 2 | 60% |  |  | % of project budget to be spent for milestone achievement. Can be entered at an individual project level below.
| Payment delay Initial Funding | 1 |  |  | Months delay from requested payment to actual payment
| Payment delay: Tranche 1 Milestones | 1 |  |  | Months delay from milestone achievement to payment
| Payment delay: Tranche 2 Milestones | 1 |  |  | Months delay from milestone achievement to payment
2 | Project Cash Flow Profile |  |  |  |  | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
| Quarter |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
2.1 | [Enter project name]
| Start date | 2020-11-01 | Project start date
| End date | 2022-03-01 | Project end date
| Allocated funding | 10 | Project budget
| Activity Flag |  |  |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Estimated cash outflow |  |  |  |  | 0 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824
| Cumulative cash outflow |  |  |  |  | 0 | 0.58824 | 1.1765 | 1.7647 | 2.3529 | 2.9412 | 3.5294 | 4.1176 | 4.7059 | 5.2941 | 5.8824 | 6.4706 | 7.0588 | 7.6471 | 8.2353 | 8.8235 | 9.4118 | 10
| Milestone Spend threshold %: Tranche 1 | 40%
| Milestone Spend threshold $: Tranche 1 | 4
| Milestone Flag: Tranche 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Milestone Spend threshold %: Tranche 2 | 60%
| Milestone Spend threshold $: Tranche 2 | 6
| Milestone Flag: Tranche 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 2 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2.2 | [Enter project name]
| Start date | 2020-12-01 | Project start date
| End date | 2022-03-01 | Project end date
| Allocated funding | 4 | Project budget
| Activity Flag |  |  |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Estimated cash outflow |  |  |  |  | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
| Cumulative cash outflow |  |  |  |  | 0 | 0 | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4
| Milestone Spend threshold %: Tranche 1 | 40%
| Milestone Spend threshold $: Tranche 1 | 1.6
| Milestone Flag: Tranche 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Milestone Spend threshold %: Tranche 2 | 60%
| Milestone Spend threshold $: Tranche 2 | 2.4
| Milestone Flag: Tranche 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 2 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2.3 | [Enter project name]
| Start date | 2020-10-01 | Project start date
| End date | 2022-03-01 | Project end date
| Allocated funding | 3 | Project budget
Activity Flag | bar: 2020-10-01 to 2022-03-01
| Estimated cash outflow |  |  |  |  | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667
| Cumulative cash outflow |  |  |  |  | 0.16667 | 0.33333 | 0.5 | 0.66667 | 0.83333 | 1 | 1.1667 | 1.3333 | 1.5 | 1.6667 | 1.8333 | 2 | 2.1667 | 2.3333 | 2.5 | 2.6667 | 2.8333 | 3
| Milestone Spend threshold %: Tranche 1 | 40%
| Milestone Spend threshold $: Tranche 1 | 1.2
| Milestone Flag: Tranche 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Milestone Spend threshold %: Tranche 2 | 60%
| Milestone Spend threshold $: Tranche 2 | 1.8
| Milestone Flag: Tranche 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 2 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2.4 | [Enter project name]
| Start date | 2020-12-01 | Project start date
| End date | 2022-02-01 | Project end date
| Allocated funding | 2 | Project budget
| Activity Flag |  |  |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Estimated cash outflow |  |  |  |  | 0 | 0 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0
| Cumulative cash outflow |  |  |  |  | 0 | 0 | 0.13333 | 0.26667 | 0.4 | 0.53333 | 0.66667 | 0.8 | 0.93333 | 1.0667 | 1.2 | 1.3333 | 1.4667 | 1.6 | 1.7333 | 1.8667 | 2 | 2
| Milestone Spend threshold %: Tranche 1 | 40%
| Milestone Spend threshold $: Tranche 1 | 0.8
| Milestone Flag: Tranche 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Milestone Spend threshold %: Tranche 2 | 60%
| Milestone Spend threshold $: Tranche 2 | 1.2
| Milestone Flag: Tranche 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 2 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2.5 | [Enter project name]
| Start date | 2020-10-01 | Project start date
| End date | 2021-05-01 | Project end date
| Allocated funding | 1 | Project budget
| Activity Flag |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimated cash outflow |  |  |  |  | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative cash outflow |  |  |  |  | 0.125 | 0.25 | 0.375 | 0.5 | 0.625 | 0.75 | 0.875 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Milestone Spend threshold %: Tranche 1 | 40%
| Milestone Spend threshold $: Tranche 1 | 0.4
| Milestone Flag: Tranche 1 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Milestone Spend threshold %: Tranche 2 | 60%
| Milestone Spend threshold $: Tranche 2 | 0.6
| Milestone Flag: Tranche 2 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment Flag: Tranche 2 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
End

## Output
Three Waters Stimulus Funding - Cash Flow Profile
| Error Check | OK
| Funding Shortfall Check | OK
| Max Funding Shortfall | 0
1 | Programme Cash Flow Profile
Cash Flow Profile
| $ | Assumptions | 2020-10-31 | 2020-11-30 | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | Total | Check
|  | Quarter | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
| Opening Cash |  | 0 | 9.7083 | 8.8284 | 7.5652 | 6.302 | 5.0387 | 3.7755 | 4.4723 | 3.209 | 2.0708 | 4.9325 | 3.7943 | 2.6561 | 5.3578 | 4.2196 | 3.0814 | 1.9431 | 0.8049 | 0 | 0
Cash Outflows:
| [Enter project name] |  | 0 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 0.58824 | 10 | 0
| [Enter project name] |  | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 4 | 0
| [Enter project name] |  | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 3 | 0
| [Enter project name] |  | 0 | 0 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0 | 2 | 0
| [Enter project name] |  | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Total |  | -0.29167 | -0.8799 | -1.2632 | -1.2632 | -1.2632 | -1.2632 | -1.2632 | -1.2632 | -1.1382 | -1.1382 | -1.1382 | -1.1382 | -1.1382 | -1.1382 | -1.1382 | -1.1382 | -1.1382 | -1.0049 | -20 | 0
Funding:
| Upfront payment |  | 10 | [17 empty] | 10 | 0
| Milestones: [Enter project name] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0
| Milestones: [Enter project name] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0
| Milestones: [Enter project name] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0
| Milestones: [Enter project name] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0
| Milestones: [Enter project name] |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0
| Final payment | [18 empty] | 0.2 | 0.2 | 0
| Total |  | 10 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0 | 0 | 4 | 0 | 0 | 3.84 | 0 | 0 | 0 | 0 | 0.2 | 20 | 0
| Net Cash Flow |  | 9.7083 | -0.8799 | -1.2632 | -1.2632 | -1.2632 | -1.2632 | 0.69676 | -1.2632 | -1.1382 | 2.8618 | -1.1382 | -1.1382 | 2.7018 | -1.1382 | -1.1382 | -1.1382 | -1.1382 | -0.8049 | 0 | 0
| Closing Cash |  | 9.7083 | 8.8284 | 7.5652 | 6.302 | 5.0387 | 3.7755 | 4.4723 | 3.209 | 2.0708 | 4.9325 | 3.7943 | 2.6561 | 5.3578 | 4.2196 | 3.0814 | 1.9431 | 0.8049 | 0 | 0 | 0
| Funding shortfall check |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % of total cash spent |  | 1.458% | 5.858% | 12.17% | 18.49% | 24.81% | 31.12% | 37.44% | 43.75% | 49.45% | 55.14% | 60.83% | 66.52% | 72.21% | 77.9% | 83.59% | 89.28% | 94.98% | 100%
| % of total cash received |  | 50% | 50% | 50% | 50% | 50% | 50% | 59.8% | 59.8% | 59.8% | 79.8% | 79.8% | 79.8% | 99% | 99% | 99% | 99% | 99% | 100%
End

## Lists (hidden)
Project Dates | Quarter
2020-10-01
2020-11-01
2020-12-01 | 1
2021-01-01
2021-02-01
2021-03-01 | 1
2021-04-01
2021-05-01
2021-06-01 | 1
2021-07-01
2021-08-01
2021-09-01 | 1
2021-10-01
2021-11-01
2021-12-01 | 1
2022-01-01
2022-02-01
2022-03-01 | 1